## new requirements
Module ID | Module Name | Requirement ID | Requirement Description
M-1 | Login | BR-1 | Enter valid username/password
M2 | View reimbursement | BR-2 | View all reimbursements
M3 | Filter Reimbursement request | BR-3 | Filter Reimbursement request by status
M4 | Create Reimbursement Request | BR-4 | Create reimbursement request as an user
M5 | Approve/Deny Reimbursement Request | BR-5 | Approve / Deny and users' pending reimbursement requests

## new-test-scenario
Test Scenario ID | Test Scenario | Requirement ID
T-1 | username is valid, password is valid | BR-1
T-2 | Username is valid, password is invalid | BR-1
T-3 | username is invalid, password is valid | BR-1
T-4 | usernamer is invalid, password is invalid | BR-1
T-5 | finance manager username is valid, password is valid | BR-1
T-6 | finance manager username is valid, password is invalid | BR-1
T-7 | finance manager username is invalid, password is valid | BR-1
T-8 | finance manager username is invalid, password is invalid | BR-1
T-9 | User when loggen in, go to the view all reimbursement page | BR-2
T-10 | Finance manager when logged in, go to the view all users reimbursement page | BR-2
T-11 | After valid login, I am able to see the user page with the specific logged in user reimbursement details displayed in table format | BR-3
T-12 | After valid login, Iam able to see the finance manager's page with all users' reimbursement details displayed in table format | BR-3
T-13 | While in user page, when I click 'Create Reimbursement' button, I am taken to Create Reimbursement page form | BR-4
T-14 | When in create reimbursement page and I enter valid amount, and description, I want to add reimbrusement request. | BR-4
T-15 | When in create reimbursement page and I enter receipts along with other details, I want to add reimbrusement request. | BR-4
T-16 | While in finance manger page, I can view all users' reimbursement request and approve/deny the pending requests | BR-5
T-17 | While in finance manger page, I can view all users' reimbursement request and approve/deny the pending requests | BR-5

## new-test-case
Test Case ID | Test Case Description | Test Steps | Test Data | Expected Results | Actual Results | Pass/Fail
TC1 | while logging in as a user, a valid login and valid password is given | 1. open the web browser and go to login page 2. Type in the correct username and correct password 3. Click the login button | username =Carol88 password = …... | I can view my past requests and add new reimbursement requests | I am able to view my past requests and add new reimbursement requests | PASS
TC2 | while logging in as a user, a valid login and invalid password is given | 1. open the web browser and go to login page 2. Type in the correct username and incorrect password 3. Click the login button | username =Carol88 password = ……... | Error message with text "Invalid username and/or password" will be shown | Error message with text "Invalid username and/or password" was not shown | FAIL
TC3 | while logging in as a user, an invalid login and valid password is given | 1. open the web browser and go to login page 2. Type in the incorrect username and correct password 3. Click the login button | username =Abcd password =…… | Error message with text "Invalid username and/or password" will be shown | Error message with text "Invalid username and/or password" was not shown | FAIL
TC4 | while logging in as a user, an invalid login and invalid password is given | 1. open the web browser and go to login page 2. Type in the incorrect username and incorrect password 3. Click the login button | username =Abcd password = ……… | Error message with text "Invalid username and/or password" will be shown | Error message with text "Invalid username and/or password" was not shown | FAIL
TC5 | while logging in as a finance manager, a valid login and valid password is given | 1. open the web browser and go to login page 2. Type in the correct username and correct password 3. Click the login button | username =Siju78 password = …... | I can manage and view all reimbursements for all employees | I am able to manage and view all reimbursements for all employees | PASS
TC6 | while logging in as a finance manager, a valid login and invalid password is given | 1. open the web browser and go to login page 2. Type in the correct username and incorrect password 3. Click the login button | username =Siju78 password = ……... | Error message with text "Invalid username and/or password" will be shown | Error message with text "Invalid username and/or password" was not shown | FAIL
TC7 | while logging in as a finance manager, an invalid login and valid password is given | 1. open the web browser and go to login page 2. Type in the incorrect username and correct password 3. Click the login button | username =Abcd password =…… | Error message with text "Invalid username and/or password" will be shown | Error message with text "Invalid username and/or password" was not shown | FAIL
TC8 | while logging in as afinance manager, an invalid login and invalid password is given | 1. open the web browser and go to login page 2. Type in the incorrect username and incorrect password 3. Click the login button | username =Abcd password = ……… | Error message with text "Invalid username and/or password" will be shown | Error message with text "Invalid username and/or password" was not shown | FAIL
TC9 | After logging in as a user, redirected to the users page | 1. open the web browser and login as a user 2.redirected to the users page | logged in as a user | I can see the data of all of my reimbursement requests and the status of them (pending, approved, denied) | I am able to see the data of all of my reimbursement requests and the status of them (pending, approved, denied) | PASS
TC10 | After logging in as a finance manager, redirected to the finance manager page | 1. open the web browser and login as a finance manager 2.redirected to the finance manager page | logged in as as finance manager | I can see the data of the entire company's reimbursement requests and approve/deny the requests that are pending | I am able to see the data of the entire company's reimbursement requests and approve/deny the requests that are pending | PASS
TC11 | While in users page, I am able to view user's reimbursement details in a table format. | 1. open the web browser and login as a user 2.redirected to the users page 3. view user reimbursement | currently in user's page after valid login | I want to be able to filter my past requests by status (approved, denied, pending), so that I can more easily view them | I was able to filter my past requests by status (approved, denied, pending), so that I can more easily view them | PASS
TC12 | While in finance manager page, I am able to view all users' reimbursement details in a table format and filter them based on status. | 1. open the web browser and login as a finance manager 2.redirected to the finance manager page 3. view all users' reimbursement details in table format | Currently in finance manager page after valid login | I want to be able to filter all the company employees' reimbursement details by status (approved, denied, pending), so that I can more easily view them | I was able to filter all the company employees' reimbursement details by status (approved, denied, pending), so that I can more easily view them | PASS
TC13 | At User page, I click the 'Create Reimbursement' button to access the Create Reimbursement page | 1. open the web browser and login as a user 2.redirected to the user page 3. click the 'create reimbursement' button | Currently in user page Click 'create reimbursement' button | I will be able to access the 'create reimbursement' form in create reibursement page | I will be able to access the 'create reimbursement' form in create reibursement page | PASS
TC14 | At the create reimbursement page, i add the details to create a new reimbursement | 1. open the web browser and login as a user 2.redirected to the user page 3. click the 'create reimbursement' button 4.Add valid details(amount and description 5. click the submit button | Currently in create reimbursement page Click the submit button | I want to be able to add a reimbursement request, so that they can either be approved or denied by a finance manager | I was able to add a reimbursement request, so that they can either be approved or denied by a finance manager | PASS
TC15 | At the create reimbursement page, i add the details and receipt to create a new reimbursement | 1. open the web browser and login as a user 2.redirected to the user page 3. click the 'create reimbursement' button 4.Add valid details(amount, description) and receipts 5. click the submit button | Currently in create reimbursement page Upload receipt for reimbursement Click the submit button | I want to be able to add a reimbursement request along with receipt, so that they can either be approved or denied by a finance manager | I was not able to add a reimbursement request along with receipt, so that they can either be approved or denied by a finance manager | FAIL
TC16 | At the finance manager page, I can view all users' reimbursement requests and approve/deny all pending requests | 1. open the web browser and login as a finance manager 2.redirected to the finance manager page 3. Search filter for pending status 4. Click either Approve or Deny radio button | Currently in finance manager page status=pending Approve/Deny pending status | I want to be able to approve/deny a pending reimbursement request, so that I can proceed with transferring money to the employee if the reimbursement is approved or not if it's denied | I was able to approve/deny a pending reimbursement request, so that I can proceed with transferring money to the employee if the reimbursement is approved or not if it's denied | PASS
T-17 | At the finance manager page, I can view all users' reimbursement requests and approve/deny all pending requests with the approve/deny button | 1. open the web browser and login as a finance manager 2.redirected to the finance manager page 3. Search filter for pending status 4. Click either Approve or Deny radio button"anager page 3. Search filter for pending status 4. Click either Approve or Deny radio button | Currently in finance manager page status=pending Approve/Deny pending status | When I click on Approve/Deny radio button, the status changes and the buttons should be disabled | When I click on Approve/Deny radio button, the status changes but the buttons was disabled | FAIL

## new-Req-Traceability Matrix
Test Case ID | Test Scenario ID | Requirement ID
TC-1 | T-1 | BR-1
TC-2 | T-2 | BR-1
TC-3 | T-3 | BR-1
TC-4 | T-4 | BR1
TC-5 | T-5 | BR1
TC-6 | T-6 | BR1
TC-7 | T-7 | BR1
TC-8 | T-8 | BR1
TC-9 | T-9 | BR2
TC-10 | T-10 | BR2
TC-11 | T-11 | BR3
TC-12 | T-12 | BR3
TC-13 | T-13 | BR4
TC-14 | T-14 | BR4
TC-15 | T-15 | BR4
TC-16 | T-16 | BR-5
TC-17 | T-17 | BR-5

## new-defect-report
Defect ID | Test Case ID | Defect Description | Steps | Detected By | Date Raised | Assigned to | Status | Fixed By | Date Closed | Severity | Priority
2. Keep username input blank (fill out other fields if you want)
3. Click on Submit
D-1 | TC-2,TC-3,TC-4,TC-6,TC-7,TC-8 | When the user or the Finance manager tries to login with wrong username/password, the error message"Invalid username/password" is not shown | 1. open the web browser and login with a wrong username /finance manager 2. click the login button | Siju | 2022-07-28 | Siju | Open |  |  | Major | Medium
D-2 | TC-15 | When adding a reimbursement request, the user is not able to upload receipts | 1. open the web browser and login as a user 2.redirected to the user page 3. click the 'create reimbursement' button 4.Add valid details(amount, description) and receipts 5. click the submit button | Shushmita | 2022-07-28 | Shushmita | Open |  |  | Minor | Medium
D-3 | TC-17 | When the finance manager cliick on Approve/Deny radio button, the status changes but the buttons do not disappear/disable | 1. open the web browser and login as a finance manager 2.redirected to the finance manager page 3. Search filter for pending status 4. Click either Approve or Deny radio button | Shushmita | 2022-07-28 | Shushmita | Open |  |  | Major | Medium